## Team-4 Program Plan
|  |  | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-08 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-14
Milstone | Task | Person
Milestone 1 Project Plan Report | Gnatt Chart | Bryan | [61 empty] | WE ARE HERE --> | [5 empty] | Online Quiz! | [6 empty] | Team 4 Personal Paper Presentations
Report 1
| Notes / file system org. | Nick
Report 1
| Meeting/info organization | Santhoshini
Report 1
| Tools investigation | Kishan
Report 1
Milestone 2 Requirement Report | Tech Requirments | Bryan
Report
| Acceptance Criteria | Nick
Report
| Requirements | Santhoshini
Report
| Validation Plan | Kishan
Report
Milestone 3 Design Report | Architectural Design | Bryan
Report
| Sequence Diagram | Nick
Report
| User Interface | Santhoshini
Report
| Database Design | Kishan
Report
Milestone 4 Test Plan Report | Risk Plan | Bryan
Report
| Goals / Exit Criteria | Nick
Report
| Resource / Schedule | Santhoshini
Report
| Test Process / Methods | Kishan
Report
DEMO Final Presenation | Code / Test | Bryan
Present
| Code / Test | Nick
Present
| Code / Test | Santhoshini
Present
| Code / Test | Kishan
Present
Lectures
Individual Paper | [70 empty] | Individual Paper Research and Presentation
Legend | Due date | [62 empty] | WE ARE HERE -->
Meeting
Action